## Sheet1
SL # | Changes | Module | Description | Assaigned | Status | Start Date | End Date
1 | Layouts | Generic | Page to utilize full browser window..no margins on navbar/responsive (not fixed width) |  | Done
2 | Navabar | Generic | CSS_ please use combination of color/background and Client logo (supplied) |  | Done
3 | Font | Generic | Oakes webfont (supplied) |  | In Progress
4 | Footer | Generic | Combination color background with Client seal (supplied) |  | Done
5 | Search | Generic | Search key words often return data this is no longer valid, Forum, Blog and videos that have been removed. Courses that have been removed |  | In Progress
6 | Carousel images | Home | Reduce height by 1/3
7 | Content cards | Home | Please use dynamic CSS styled image/text hover effect
8 | Content card Icons/images | Home |  |  | Hold On
9 | Search | Home | Please add Search for a Course
10 | Main Navar | Home | Make sticky on scroll
11 | Three columns for training pathways | Home | No data pulled. Text editor to add descriptions, links, tables and images; text color
12 | Three columns for webinars, Workplace, News | Home | Upcoming Webinars: Pull data for first 7 webinars from course schedule C21 Workplace: pull from C21 FB workplace C21U News: Manually add text. Auto date stamp update. Prefer text limit to title of news, auto add More.. link to open model for full news item
13 | News card | Home | Auto add date
14 | Upcoming webinars | Home | Auto display next 7 days of courses from course schedule
15 | Video strip | Home | Most popular videos, title, description
16 | Over all page | Browse Courses | Use Client coloring for background, title bar and course titles – No blue coloring for links and icons |  | Done
17 | Blue filter bar | Browse Courses | Change to C21 coloring |  | Done
18 | Filters | Browse Courses | Filters: (this may change, will confirm) Broker/managers Sales Associates Coaching Recruiting NAR certification DASH ZAP Commercial |  | By Configure
19 | Sort By | Browse Courses | Title & Audience |  | Done
20 | CE Shop page | Browse Courses | Any changes needed? Waiting for response from C21 |  | Hold
21 | Topic images for all sections and subsections | How to Video | Static images for all topics (will provide images need size) |  | Hold
22 | Title | How to Video | Change from black background white title, to C21 coloring |  | Done
23 | Favorites | How to Video | Unable to remove a favorited video from favorites folder |  | In Progress
24 | Title and link text | Course Schedule | Please remove all blue and use C21 coloring |  | Done
25 | Adding course | Course Schedule | Ability to copy an existing course (then edit) |  | Not understand
26 | Title hover | Course Schedule | Change from black to c21 coloring |  | Done
27 | Nav title | Course Resources | Change to Course Resources |  | Done
28 | Blue column header | Course Resources | Change to c21 coloring |  | Done